## Sheet1
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-5/5/2024 , BRANCH NAME - frontend-v2 ,TESTED (Auth Pages)
submitted by :Sudhanshu Tripathi
TC- 1 | Sudhanshu | 2024-05-05 | We can acces USER Dashboard directly without login & signup | 2 | FRONTEND TEAM | User Interface | YES |  | CLOSED
TC- 02 | Sudhanshu | 2024-05-05 | We can acces CARETAKER Dashboard directly without login & signup | 2 | FRONTEND TEAM | User Interface | YES |  | CLOSED
TC- 3 | Sudhanshu | 2024-05-05 | Password Update is not working | 2 | FRONTEND TEAM | User Interface |  |  | CLOSED
TC- 4 | Sudhanshu | 2024-05-05 | Enter a new password that meets the minimum requirements missing. | 2 | FRONTEND TEAM | User Interface | YES |  | CLOSED
TC- 5 | Sudhanshu | 2024-05-05 | There is no option for logout | 2 | FRONTEND TEAM | User Interface | YES |  | CLOSED
TC- 6 | Sudhanshu | 2024-05-05 | Show place of 6 digit otp send and verify 5 digit otp | 2 | FRONTEND TEAM | Logical | YES |  | CLOSED
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-16/5/2024 , BRANCH NAME - frontend-v4 ,TESTING frontend defects
submitted by : Saikat Saha
TC- 1 | Saikat Saha | 16/5/2024 | when there is not data for the graph you should be showing image. conditional rendering is missing | 3 | FRONTEND TEAM | User Interface | YES
TC- 02 | Saikat Saha | 16/5/2024 | proportions of cards are not similar. welcome back card width should be 50% to 60% | 3 | FRONTEND TEAM | User Interface | YES
TC- 3 | Saikat Saha | 16/5/2024 | at bottom right list of reminders goals and habits the tabs are not selectable and the selected tab(by default reminder) should have a underline indicating active tab. | 3 | FRONTEND TEAM | User Interface | YES
TC- 4 | Saikat Saha | 16/5/2024 | add responsiveness from the start instead of making it as a another task. | 3 | FRONTEND TEAM | User Interface | YES
TC- 5 | Saikat Saha | 16/5/2024 | when signin/signup the message in the toast should be the message from backend. (optionally you can add your own message along with the backend message) | 3 | FRONTEND TEAM | User Interface | YES
TC- 6 | Saikat Saha | 16/5/2024 | at profile as we are currently not taking any image from users the profile will contain a random color which matches with our theme and the intial lettrs or user name should be there in the profile . | 3 | FRONTEND TEAM | User Interface | YES
TC- 7 | Saikat Saha | 16/5/2024 | in the graph the year dropdown is missing | 3 | FRONTEND TEAM | User Interface | YES
TC- 8 | Saikat Saha | 16/5/2024 | at bottom right list of reminders goals and habits the filter button is not working | 3 | FRONTEND TEAM | User Interface | YES
TC- 9 | Saikat Saha | 16/5/2024 | The calender dates are not color coded with red and yellow (red for in not started, yellow for in progress) | 3 | FRONTEND TEAM | User Interface | YES
TC- 10 | Saikat Saha | 16/5/2024 | The "Profile" is not mentioned in profile card and the background color of user details should not be white, should be same as the card background color | 3 | FRONTEND TEAM | User Interface | YES
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-21/5/2024 , BRANCH NAME - backend-api ,TESTING backend api
submitted by : Saikat Saha
TC- 1 | Saikat Saha | 16/5/2024 | Caretaker Registration | 3 | Sohail | Logical | Logic of the function updated | 21/05/2024 | Closed | { "status": "failed", "message": "\"enteredOtp\" is not allowed. \"role\" is not allowed" }
TC- 02 | Saikat Saha | 16/5/2024 | Caretaker login | 3 | Sohail | Logical | Logic of the function updated | 21/05/2024 | Closed | { "status": "failed", "message": "\"role\" is not allowed" }
TC- 3 | Saikat Saha | 16/5/2024 | Reset Password using Email | 3 | Sohail | Logical | Logic of the function updated | 21/05/2024 | Closed | { "status": "failed", "message": "\"otp\" is required. \"role\" is not allowed" }
TC- 4 | Saikat Saha | 16/5/2024 | caretaker create goal for user | 3 | Sohail | Logical | Logic of the function updated | 21/05/2024 | Closed | { "status": "failed", "message": "Only caretakers can access this endpoint" }
TC- 5 | Saikat Saha | 16/5/2024 | updateReminders | 3 | Sohail | Logical | Logic of the function updated | 21/05/2024 | Closed | { "status": "failed", "message": "\"_id\" is required. \"reminderId\" is not allowed" }
TC- 6 | Saikat Saha | 16/5/2024 | deleteReminder | 3 | Sohail | Logical | Logic of the function updated | 21/05/2024 | Closed | { "status": "failed", "message": "invalid signature" }
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-29/5/2024 , BRANCH NAME - notification-integration ,TESTING user routes
submitted by : Saikat Saha
TC- 1 | Saikat Saha | 29/5/2024 | The Text and Image is overlapping in login page | 4 | FRONTEND TEAM | User Interface
TC- 2 | Saikat Saha | 29/5/2024 | The Remember me button doing nothing | 4 |  | Standards |  |  |  | if the remember me button is not working this should be removed
TC- 3 | Saikat Saha | 29/5/2024 | There is no buffer page or loading page while sending otp or creating account | 4 | FRONTEND TEAM | User Interface | YES |  |  | Because of no loading page the user could be confused
TC- 4 | Saikat Saha | 29/5/2024 | There is no dropdown button on selecting role or gender . this might be confusing | 4 | FRONTEND TEAM | User Interface | YES
TC- 4 | Saikat Saha | 29/5/2024 | In the sign in page there should be a password view option in password enter section | 4 | FRONTEND TEAM | User Interface
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-29/5/2024 , BRANCH NAME - notification-integration ,TESTING User dashboard
submitted by : Hetvi Vaghani
TC-1 | Hetvi Vaghani | 29/5/2024 | In the Goal progress drop down menu for selecting year is not created | 4 |  | User Interface | YES
TC-2 | Hetvi Vaghani | 29/5/2024 | Sorting button above the calander for goal ,reminders and habits is not created yet | 4 | FRONTEND TESM | User Interface | YES
TC-3 | Hetvi Vaghani | 29/5/2024 | In about user box edit profile button is not working | 4 | FRONTEND TEAM | User Interface | YES
TC-4 | Hetvi Vaghani | 29/5/2024 | Reminder, Goal and habits is not changing with selected date from calender | 4 | FRONTEND TEAM | Logical | YES
TC-5 | Hetvi Vaghani | 29/5/2024 | When no reminders are added there should be a button as "add reminder " in that section is not added | 4 | FRONTEND TEAM | User Interface | YES
TC-6 | Hetvi Vaghani | 29/5/2024 | The profile section should not show random person pic in profile picture section | 4 | FRONTEND TEAM | User Interface | YES
TC-7 | Hetvi Vaghani | 29/5/2024 | The profile section is not showing user name | 4 | FRONTEND TEAM | Logical | YES
TC-8 | Hetvi Vaghani | 29/5/2024 | In the "about user" section the "Edit profile" button is not working | 4 | FRONTEND TEAM | Logical | Yes
TC-9 | Hetvi Vaghani | 29/5/2024 | The circle progress and the progress bar is not matching | 4 |  | Logical
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-29/5/2024 , BRANCH NAME - notification-integration ,TESTING User Goal page
submitted by : Saikat Saha
TC-1 | Saikat Saha | 29/5/2024 | The triple dots are not working | 4 | FRONTEND TEAM | Logical | removed
TC-2 | Saikat Saha | 29/5/2024 | The elements are not covering the whole page | 4 |  | Logical
TC-3 | Saikat Saha | 29/5/2024 | The select all button is not working | 4 |  | Logical
TC-4 | Saikat Saha | 29/5/2024 | In the goal when 2nd goal is added its overlapping with the reminder section and other goals are not visible | 4 | FRONTEND TEAM | Logical | Update the code
TC-5 | Saikat Saha | 29/5/2024 | There is only one goal or one reminder | 4 |  | Logical
TC-6 | Saikat Saha | 29/5/2024 | The sections is not expending when new goals or reminders or habits are added | 4 |  | Logical
TC-7 | Saikat Saha | 29/5/2024 | Habit section also should have three dots where the delete or update options will be visible | 4 |  | Logical
TC-8 | Saikat Saha | 29/5/2024 | The End date is wrong | 4 |  | Logical
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-30/5/2024 , BRANCH NAME - notification-integration ,TESTING Caretacker dashboard
submitted by : Hetvi Vaghani
TC-1 | Hetvi Vaghani | 30/5/2024 | Column name is missing in assign and unassigned user table | 4 | FRONTEND TEAM | User Interface | YES
TC-2 | Hetvi Vaghani | 30/5/2024 | There are to much space after the cards | 4 | FRONTEND TEAM | User Interface | YES
TC-3 | Hetvi Vaghani | 30/5/2024 | All the users are getting assigend at the same time | 4 | FRONTEND TEAM | Logical

## sheet2
TC-4 | Hetvi Vaghani | 30/5/2024 | User update section is not updating the status | 4 |  | Logical
TC-5 | Hetvi Vaghani | 30/5/2024 | User list is showing same profile picture for every user | 4 |  | User Interface
TC-6 | Hetvi Vaghani | 30/5/2024 | After assigning goal to the user from add goal page it is not updating in dashboard page | 4 |  | Logical
TC-7 | Akshay H R | 2024-02-06 | No notification is showing in caretaker page | 4 |  | Logical
TC-8 | Akshay H R | 2024-02-06 | Goals are not updating in caretaker page | 4 |  | Logical
TC-9 | Akshay H R | 2024-02-06 | goal updation is not user specified | 4 |  | Logical
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-30/5/2024 , BRANCH NAME - Frontend-remainder ,User Page
submitted by : Akshay H R
TC-1 | Akshay H R | 2024-02-06 | profile picture is showing Random person picture | 4 |  | Logical
TC-2 | Akshay H R | 2024-02-06 | Goal progress is not matching | 4 |  | Logical
TC-3 | Akshay H R | 2024-02-06 | In About user section edit button is not working | 4 |  | Logical
TC-4 | Akshay H R | 2024-02-06 | Notification panel is not fixed | 4 |  | Logical
TC-5 | Akshay H R | 2024-02-06 | Profile picture uploading option is nothere | 4 |  | Logical
TC-6 | Akshay H R | 2024-02-06 | Email is not updating in user profile | 4 |  | Logical
TC-6 | Akshay H R | 2024-02-06 | Email updation requires otp to update email | 4 |  | Logical
TC-7 | Akshay H R | 2024-02-06 | In goal progress Bar the Jan,sep,Nov Months, are not listed | 4 |  | Logical
TC-8 | Akshay H R | 2024-02-06 | In the target page goals Add remainder and Habits, not showing propery | 4 |  | Logical
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-02/5/2024 ,- Login Page
submitted by : Akshay H R
TC-1 | Akshay H R | 2024-02-06 | In login Page the rightand side image , texts are overlapping on image | 4 |  | User Interface
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DATE-5/6/2024 , BRANCH NAME - master ,TESTING unfixed bugs
submitted by : Saikat Saha
TC-1 | Saikat Saha | 2024-05-06 | Profile picture uploading option is not there | 4 |  | Logical
TC-2 | Saikat Saha | 2024-05-06 | Email updation requires otp to update email | 4 |  | Logical
TC-3 | Saikat Saha | 2024-05-06 | The select all button target page goal , reminder and habit section is not working | 4 |  | Logical
TC-4 | Saikat Saha | 2024-05-06 | profile picture is showing Random person picture | 4 |  | User Interface
TC-5 | Saikat Saha | 2024-05-06 | In goal progress Bar the Jan,sep,Nov Months, are not listed | 4 |  | User Interface
TC-6 | Saikat Saha | 2024-05-06 | added reminders are not showing in the target page | 4 |  | User Interface
TC-7 | Saikat Saha | 2024-05-06 | The Remember me button doing nothing | 4 |  | Standards
TC-8 | Saikat Saha | 2024-05-06 | No notification is showing in caretaker page | 4 |  | Logical
TC-9 | Saikat Saha | 2024-05-06 | Caretaker edit profile is showing nothing | 4 |  | Logical